## Door
[6 empty] | PROJECT NAME | WLA - B13 |  | GENERAL CONTRACTOR |  | Walton Construction inc. |  | DATE OF PREPARATION |  | 2026-06-11
[6 empty] | LOCATIONS |  |  | SUBCONTRACTOR |  | KAPTIVE C&P
Identification & Site Logic | [5 empty] | Technical Assessment Matrix | [16 empty] | Pathology
Photo | Inspection Level | Room Name | Access Status | ID Door | Door Origin | Door Type | Door - Current Status | Door Material | Door - Recommended Action | Door - Notes | Frame - Current Status | Frame - Recommended Action | Frame - Notes | Hinges - Current Status | Hinges - Recommended Action | Transom - Current Status | Transom - Function | Transom - Recommended Action | Transom - Notes | Door handle - Current Status | Door handle - Recommended Action | Automatic closing arm - Current Status | Technical Notes | Evaluation score | Priority
| Basement Level | MECH ROOM AND STORAGE | Accessible | D0001 | Original Door | Double Door | Existing | Metal | Clear/Restore | Tier 2 | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Not Operable | Clear/Restore | RFI if we putting glass or staying metal gate | Missing | Repair/Make | None |  | 25 | Priority 2
| Basement Level | MECH ROOM AND STORAGE | Accessible | D0002 | Original Door | Single Door | Missing | Wood | Repair/Make | Door missing | Existing | Clear/Restore |  | Missing | Repair/Make | None | Not Operable | None |  | Missing | Repair/Make | None | Door missing | 41 | Priority 4
| Basement Level | MECH ROOM AND STORAGE | Accessible | D0004 | Original Door | Single Door | Existing | Wood | Clear/Restore | Tier 3 Best | Existing | Clear/Restore |  | Existing | Clear/Restore | None | Not Operable | None |  | Missing | Repair/Make | None |  | 21 | Priority 2
| Basement Level | MECH ROOM AND STORAGE | Accessible | D0005 | Original Door | Single Door | Existing | Wood | Clear/Restore | Tier 3 Best | Existing | Clear/Restore |  | Existing | Clear/Restore | None | Not Operable | None |  | Missing | Repair/Make | None |  | 21 | Priority 2
| Basement Level | MECH ROOM AND STORAGE | Accessible | D0006 | Original Door | Single Door | Existing | Wood | Repair/Make | Tier 2 | Missing | Clear/Restore |  | Existing | Clear/Restore | None | Not Operable | None |  | Missing | Repair/Make | None |  | 35 | Priority 3
| Basement Level | MECH ROOM AND STORAGE | Accessible | D0007 | Not applicable | Single Door | Missing | RFI closet not marked in the plans | Repair/Make | RFI | Existing | Clear/Restore |  | Missing | Repair/Make | None | Not Operable | None |  | Missing | Repair/Make | None | RFI door frame no door and not in the plans | 41 | Priority 4
| Basement Level | MECH ROOM AND STORAGE | Accessible | D0008 | Not applicable | Single Door | Missing | Wood | Repair/Make | RFI door not in the plans | Existing | Clear/Restore |  | Missing | Repair/Make | None | Not Operable | None |  | Missing | Repair/Make | None | RFI Door not in the plans | 41 | Priority 4
| Basement Level | MECH ROOM AND STORAGE | Accessible | D0009 | Not applicable | Single Door | Missing | Wood | Repair/Make | RFI Door not in the plans | Existing | Clear/Restore |  | Missing | Repair/Make | None | Not Operable | None |  | Missing | Repair/Make | None | RFI Door not in the plans | 41 | Priority 4
| Basement Level | MECH ROOM AND STORAGE | Accessible | D0003 | Original Door | Single Door | Existing | Wood | Clear/Restore | Tier 2 | Existing | Clear/Restore |  | Existing | Clear/Restore | None | Not Operable | None |  | Missing | Repair/Make | None |  | 21 | Priority 2
| Level 1 | CANTEEN AND PATRIOT STORE | Accessible | D1001 | New Door | Double Door | Missing | Metal | Repair/Make |  | Missing | Repair/Make |  | Missing | Repair/Make | None | Not Operable | None |  | Missing | Repair/Make | None | New door new everything | 52 | Priority 4
| Level 1 | FITNESS | Accessible | D1002 | New Door | Double Door | Missing | Metal | Repair/Make |  | Missing | Repair/Make |  | Missing | Repair/Make | None | Not Operable | None |  | Missing | Repair/Make | None |  | 52 | Priority 4
| Level 1 | GRAND HALL | Accessible | D1003 | Original Door | Double Door | Missing | Metal | Repair/Make |  | Missing | Repair/Make |  | Missing | Repair/Make | None | Not Operable | None |  | Missing | Repair/Make | None | New door new everything | 52 | Priority 4
| Level 1 | FITNESS | Demolished or Lost | D1004 | New Door | [18 empty] | 0 | Not Verifiable
| Level 1 | Other | Accessible | D1006 | New Door | Single Door | Missing | Wood | Repair/Make | Door missing | Existing | Clear/Restore |  | Missing | Repair/Make | Existing | Not Operable | Clear/Restore |  | Missing | Repair/Make | None | Door is missing frame is there | 45 | Priority 4
| Level 1 | STORAGE | Accessible | D1009 | Original Door | Single Door | Existing | Wood | Clear/Restore | Tier 2 | Existing | Clear/Restore |  | Missing | Repair/Make | None | Not Operable | None |  | Existing | Clear/Restore | None |  | 18 | Priority 1
| Level 1 | Other | Accessible | D1010 | Original Door | Single Door | Existing | Wood | Repair/Make |  | Existing | Clear/Restore |  | Existing | Clear/Restore | None | Not Operable | None |  | Missing | Repair/Make | None | New door needed. Door tier 1 | 26 | Priority 2
| Level 1 | MENS RESTROOM | Demolished or Lost | D1011 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 1 | MENS RESTROOM | Demolished or Lost | D1012 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 1 | MENS RESTROOM | Demolished or Lost | D1013 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 1 | MENS RESTROOM | Demolished or Lost | D1014 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 1 | MENS RESTROOM | Demolished or Lost | D1015 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 1 | MENS RESTROOM | Demolished or Lost | D1016 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 1 | Other | Accessible | D1017 | Original Door | Single Door | Existing | Wood | Clear/Restore |  | Existing | Clear/Restore |  | Existing | Clear/Restore | None | Not Operable | None |  | Existing | Clear/Restore | None |  | 12 | Priority 1
| Level 1 | EAST LOBBY | Demolished or Lost | D1019 | New Door | [17 empty] | New Door. Old one was remove. | 0 | Not Verifiable
| Level 1 | WEST LOBBY | Demolished or Lost | D1020 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 1 | EAST LOBBY | Demolished or Lost | D1021 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 1 | STORAGE | Demolished or Lost | D1022 | New Door | [17 empty] | New door. Opening has to be cut | 0 | Not Verifiable
| Level 1 | STORAGE | Demolished or Lost | D1023 | New Door | [17 empty] | New door new everything and opening needs to be cut | 0 | Not Verifiable
| Level 1 | ELEC | Demolished or Lost | D1024 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 1 | WOMENS RESTROOM | Demolished or Lost | D1025 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 1 | WOMENS RESTROOM | Demolished or Lost | D1026 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 1 | WEST LOBBY | Demolished or Lost | D1028 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 1 | WOMENS RESTROOM | Demolished or Lost | D1029 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 1 | WOMENS RESTROOM | Demolished or Lost | D1030 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 1 | WOMENS RESTROOM | Demolished or Lost | D1031 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 1 | WOMENS RESTROOM | Demolished or Lost | D1032 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 1 | HALLWAY | Demolished or Lost | D1033 | New Door | [17 empty] | New door new everything and opening needs to be cut. | 0 | Not Verifiable
| Level 1 | WOMENS RESTROOM | Demolished or Lost | D1034 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 1 | WOMENS RESTROOM | Demolished or Lost | D1035 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 1 | WOMENS RESTROOM | Demolished or Lost | D1036 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 1 | WOMENS RESTROOM | Demolished or Lost | D1037 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 1 | WOMENS RESTROOM | Demolished or Lost | D1038 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 1 | WOMENS RESTROOM | Demolished or Lost | D1039 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 1 | EAST LOBBY | Demolished or Lost | D1040 | New Door | [18 empty] | 0 | Not Verifiable
| Level 1 | HALLWAY | Demolished or Lost | D1041 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 1 | HALLWAY | Demolished or Lost | D1043 | New Door | [17 empty] | New door new everything and opening needs to cut | 0 | Not Verifiable
| Level 1 | OFFICE | Demolished or Lost | D1045 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 1 | OFFICE | Demolished or Lost | D1046 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 1 | HALLWAY | Demolished or Lost | D1047 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 1 | OFFICE | Demolished or Lost | D1048 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 1 | HALLWAY | Demolished or Lost | D1049 | New Door | [17 empty] | New door new everything and opening needs to cut | 0 | Not Verifiable
| Level 1 | OFFICE | Demolished or Lost | D1050 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 1 | OFFICE | Demolished or Lost | D1051 | New Door | [17 empty] | New everything | 0 | Not Verifiable
| Level 1 | GROCERY STORE | Accessible | D1052 | New Door | Double Door | Missing | Metal | Repair/Make |  | Existing | Repair/Make |  | Missing | Repair/Make | None | Not Operable | None |  | Missing | Repair/Make | None | New door new everything | 43 | Priority 4
| Level 1 | VA SERVICES | Accessible | D1053 | Original Door | Double Door | Missing | Metal | Repair/Make |  | Missing | Repair/Make |  | Missing | Repair/Make | None | Not Operable | None |  | Missing | Repair/Make | None |  | 52 | Priority 4
| Level 1 | U.S. VETS FACILITIES AND MAINTENANCE | Accessible | D1054 | Original Door | Single Door | Existing | Metal | Clear/Restore | Tier 2 | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Not Operable | Clear/Restore |  | Missing | Repair/Make | None |  | 25 | Priority 2
| Level 1 | MECH. RM | Accessible | D1055 | Original Door | Single Door | Existing | Wood | Clear/Restore | Tier 3 | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Not Operable | Clear/Restore |  | Existing | Clear/Restore | None |  | 16 | Priority 1
| Level 1 | BIKE REPAIR AND STORAGE | Accessible | D1056 | Original Door | Single Door | Existing | Metal | Clear/Restore | Door tier 2 | Existing | Clear/Restore |  | Missing | Repair/Make | Existing | Not Operable | Clear/Restore |  | Existing | Clear/Restore | None |  | 22 | Priority 2
| Level 1 | U.S. VETS FACILITIES AND MAINTENANCE | Demolished or Lost | D1057 | New Door | [17 empty] | New door new everything and opening needs to be cut | 0 | Not Verifiable
| Level 1 | ELEC. RM | Demolished or Lost | D1058 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 1 | MECH. RM | Demolished or Lost | D1059 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 1 | MECH. RM | Accessible | D1060 | Original Door | Single Door | Existing | Metal | Repair/Make | Tier 1 | Existing | Clear/Restore |  | Existing | Clear/Restore | None | Not Operable | None |  | Missing | Repair/Make | None | Door is hallow | 26 | Priority 2
| Level 2 | 1 BEDROOM | Demolished or Lost | D2001 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2002 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2003 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2004 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2005 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2006 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2007 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2008 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2009 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2010 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2011 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2012 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Accessible | D2013 | Original Door | Double Door | Existing | Wood | Clear/Restore | Tier 2 | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Not Operable | Clear/Restore |  | Missing | Repair/Make | None | RFI door entrance to two different bed rooms | 25 | Priority 2
| Level 2 | 1 BEDROOM | Accessible | D2014 | Original Door | Double Door | Existing | Wood | Clear/Restore | Tier 2 | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Not Operable | Clear/Restore |  | Missing | Repair/Make | None | RFI entrance to two different bedrooms | 25 | Priority 2
| Level 2 | 1 BEDROOM | Accessible | D2015 | Original Door | Double Door | Existing | Wood | Clear/Restore | Tier 2 | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Not Operable | Clear/Restore |  | Missing | Repair/Make | None | RFI entrance to two different bedrooms | 25 | Priority 2
| Level 2 | 1 BEDROOM | Accessible | D2016 | Original Door | Double Door | Existing | Wood | Clear/Restore | Tier 2 | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Not Operable | Clear/Restore |  | Missing | Repair/Make | Keep | RFI entrance to two different bedrooms | 27 | Priority 2
| Level 2 | 1 BEDROOM | Demolished or Lost | D2017 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2018 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2019 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2020 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2021 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2022 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2023 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2024 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | HALLWAY | Demolished or Lost | D2025 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | HALLWAY | Demolished or Lost | D2026 | New Door | [17 empty] | RFI what kind of double door | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Accessible | D2027 | Original Door | Single Door | Existing | Wood | Clear/Restore | Tier 2 | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Operable | Clear/Restore | Paint shit | Missing | Repair/Make | None |  | 29 | Priority 2
| Level 2 | 1 BEDROOM | Accessible | D2028 | Original Door | Single Door | Existing | Wood | Clear/Restore | Tier 3 | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Operable | Clear/Restore | Paint shut | Missing | Repair/Make | None |  | 29 | Priority 2
| Level 2 | 1 BEDROOM | Accessible | D2029 | Original Door | Single Door | Existing | Wood | Clear/Restore | Tier2 | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Operable | Clear/Restore | Paint shut | Missing | Repair/Make | Keep |  | 31 | Priority 3
| Level 2 | 1 BEDROOM | Accessible | D2030 | Original Door | Single Door | Existing | Wood | Clear/Restore | Tier 3 | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Operable | Clear/Restore | Paint shut | Missing | Repair/Make | None |  | 29 | Priority 2
| Level 2 | COMMUNITY LOUNGE | Accessible | D2031 | Original Door | Single Door | Existing | Wood | Clear/Restore | Tier 2 | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Operable | Clear/Restore | Paint shut | Missing | Repair/Make | Keep |  | 31 | Priority 3
| Level 2 | COMMUNITY LOUNGE | Accessible | D2032 | Original Door | Single Door | Existing | Wood | Clear/Restore | Tier 2 | Existing | Repair/Make |  | Existing | Clear/Restore | Existing | Operable | Clear/Restore | Paint shut | Missing | Repair/Make | Keep |  | 33 | Priority 3
| Level 2 | STUDIO | Demolished or Lost | D2033 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | STUDIO | Demolished or Lost | D2034 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | LAUNDRY | Demolished or Lost | D2035 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | STUDIO | Accessible | D2037 | Original Door | Single Door | Existing | Wood | Clear/Restore | Tier 3 | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Operable | Clear/Restore | Paint shut | Missing | Repair/Make | None |  | 29 | Priority 2
| Level 2 | STUDIO | Accessible | D2038 | Original Door | Single Door | Existing | Wood | Clear/Restore | Tier2 | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Operable | Clear/Restore | Paint shut | Existing | Repair/Make | Keep |  | 27 | Priority 2
| Level 2 | ELEC. | Accessible | D2039 | New Door | Single Door | Missing | Wood | Repair/Make |  | Existing | Repair/Make |  | Missing | Repair/Make | Existing | Operable | Clear/Restore | Paint shut | Missing | Repair/Make | None | New Door New Everything | 51 | Priority 4
| Level 2 | ELEC. | Accessible | D2040 | Original Door | Single Door | Existing | Wood | Clear/Restore | Tier 2 | Existing | Repair/Make |  | Existing | Clear/Restore | Existing | Operable | Clear/Restore | Paint shut | Missing | Repair/Make | Keep |  | 33 | Priority 3
| Level 2 | HALLWAY | Demolished or Lost | D2041 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 2 | TRASH | Demolished or Lost | D2042 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | HALLWAY | Accessible | D2043 | Original Door | Double Door | Existing | Wood | Clear/Restore | Tier 3 | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Not Operable | Clear/Restore |  | Missing | Repair/Make | None |  | 25 | Priority 2
| Level 2 | HALLWAY | Accessible | D2044 | Original Door | Double Door | Existing | Wood | Clear/Restore | Tier2 | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Not Operable | Clear/Restore |  | Missing | Repair/Make | None |  | 25 | Priority 2
| Level 2 | 1 BEDROOM + DEN | Accessible | D2045 | New Door | Single Door | Missing | Wood | Repair/Make |  | Existing | Clear/Restore |  | Missing | Repair/Make | Existing | Operable | Clear/Restore | Paint shut | Missing | Repair/Make | None |  | 49 | Priority 4
| Level 2 | 1 BEDROOM + DEN | Accessible | D2046 | Original Door | Single Door | Existing | Wood | Clear/Restore | Tier2 | Existing | Repair/Make |  | Existing | Clear/Restore | Existing | Operable | Clear/Restore | Paint shut | Missing | Repair/Make | None |  | 31 | Priority 3
| Level 2 | 1 BEDROOM | Demolished or Lost | D2047 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | Other | Demolished or Lost | D2049 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | Other | Demolished or Lost | D2050 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Accessible | D2051 | Original Door | Single Door | Existing | Wood | Clear/Restore | Tier 3 | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Operable | Clear/Restore | Paint shut | Missing | Repair/Make | None |  | 29 | Priority 2
| Level 2 | 1 BEDROOM | Accessible | D2052 | Original Door | Single Door | Existing | Wood | Clear/Restore | Tier1 | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Operable | Clear/Restore | Paint shut | Missing | Repair/Make | Keep |  | 31 | Priority 3
| Level 2 | 1 BEDROOM + DEN | Demolished or Lost | D2053 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM + DEN | Demolished or Lost | D2054 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | HALLWAY | Demolished or Lost | D2055 | New Door | [18 empty] | 0 | Not Verifiable
| Level 2 | HALLWAY | Demolished or Lost | D2056 | New Door | [17 empty] | New Door New Everything. To remove window and concrete cut opening for door | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2057 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2058 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2059 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2060 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | SEATING AREA | Demolished or Lost | D2061 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2062 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2063 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2064 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Accessible | D2065 | New Door | Single Door | Existing | Wood | Clear/Restore | Tier2 | Existing | Clear/Restore |  | Existing | Repair/Make | Existing | Operable | Clear/Restore | Paint shut | Missing | Repair/Make | None |  | 31 | Priority 3
| Level 2 | 1 BEDROOM | Accessible | D2066 | Original Door | Single Door | Existing | Wood | Clear/Restore | Tier 2 | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Operable | Clear/Restore | Paint shut | Missing | Repair/Make | None |  | 29 | Priority 2
| Level 2 | 1 BEDROOM | Accessible | D2067 | Original Door | Single Door | Existing | Wood | Clear/Restore | Tier 3 Best | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Operable | Clear/Restore | Paint shut | Missing | Repair/Make | None |  | 29 | Priority 2
| Level 2 | 1 BEDROOM | Accessible | D2068 | Original Door | Single Door | Existing | Wood | Clear/Restore | Tier2 | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Operable | Clear/Restore | Paint shut | Missing | Repair/Make | Keep |  | 31 | Priority 3
| Level 2 | HALLWAY | Demolished or Lost | D2069 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 2 BEDROOM | Demolished or Lost | D2070 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 2 BEDROOM | Demolished or Lost | D2071 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 2 BEDROOM | Demolished or Lost | D2072 | New Door | [17 empty] | New door new everything | 0 | Not Verifiable
| Level 2 | 2 BEDROOM | Accessible | D2073 | Original Door | Double Door | Existing | Wood | Clear/Restore | Tier2 | Existing | Clear/Restore |  | Existing | Repair/Make | Existing | Not Operable | Clear/Restore | Glass broken | Missing | Repair/Make | None |  | 27 | Priority 2
| Level 2 | 2 BEDROOM | Demolished or Lost | D2073 | New Door | [18 empty] | 0 | Not Verifiable
| Level 2 | 2 BEDROOM | Demolished or Lost | D2074 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 2 BEDROOM | Demolished or Lost | D2076 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 2 BEDROOM | Demolished or Lost | D2077 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 2 BEDROOM | Accessible | D2078 | Original Door | Double Door | Existing | Wood | Clear/Restore | Tier 2 | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Not Operable | Clear/Restore |  | Missing | Repair/Make | None |  | 25 | Priority 2
| Level 2 | 2 BEDROOM | Demolished or Lost | D2080 | New Door | [18 empty] | 0 | Not Verifiable
| Level 2 | 2 BEDROOM | Demolished or Lost | D2081 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 2 BEDROOM | Demolished or Lost | D2082 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 2 BEDROOM | Demolished or Lost | D2084 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 2 BEDROOM | Demolished or Lost | D2085 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2086 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2088 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2089 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2090 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2091 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2092 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2093 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2094 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2095 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2096 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2097 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2099 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2100 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2101 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Demolished or Lost | D2102 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | LAUNDRY | Demolished or Lost | D2103 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | SEATING AREA | Demolished or Lost | D2104 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | OFFICE | Demolished or Lost | D2105 | New Door | [17 empty] | New Door New Everything | 0 | Not Verifiable
| Level 2 | LOBBY | Demolished or Lost | D2106 | New Door | [17 empty] | New Door New Everything Double door | 0 | Not Verifiable
| Level 2 | SEATING AREA | Accessible | D2107_1 | Original Door | Single Door | Existing | Wood | Clear/Restore | Tier 2 | Existing | Clear/Restore |  | Existing | Clear/Restore | None | Not Operable | None |  | Existing | Clear/Restore | None | Screen door | 12 | Priority 1
| Level 2 | SEATING AREA | Accessible | D2107_2 | Original Door | Single Door | Existing | Metal | Clear/Restore | Tier 2 | Existing | Clear/Restore |  | Existing | Clear/Restore | None | Not Operable | None |  | Missing | Repair/Make | None |  | 21 | Priority 2
| Level 2 | OFFICE | Accessible | D2108 | Original Door | Single Door | Existing | Metal | Clear/Restore | Tier 2 | Existing | Clear/Restore |  | Existing | Clear/Restore | None | Not Operable | None |  | Existing | Repair/Make | None | 1 broken glass. Missing one handle | 17 | Priority 1
| Roof Level | Other | Demolished or Lost | D3001 | New Door | [17 empty] | New Door New Everything Same as D2049 | 0 | Not Verifiable
| Roof Level | Other | Demolished or Lost | D3002 | New Door | [17 empty] | New Door New Everything Same as D2050 | 0 | Not Verifiable
| Roof Level | Other | Demolished or Lost | D3003 | New Door | [17 empty] | New Door New Everything Same as D2055 | 0 | Not Verifiable
| Roof Level | Other | Demolished or Lost | D3004 | New Door | [17 empty] | New Door New Everything Same as D2059 | 0 | Not Verifiable
| Roof Level | HALLWAY | Demolished or Lost | D3005 | New Door | [17 empty] | Same as D2069 | 0 | Not Verifiable
| Level 2 | 1 BEDROOM | Accessible | D2119 | Not applicable | Transom | Existing | Other | Clear/Restore | Transom | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Operable | Clear/Restore | Paint shut | Existing | Repair/Make |  |  | 25 | Priority 2
| Level 2 | 1 BEDROOM | Accessible | D2109 | Not applicable | Transom | Missing | Other | Repair/Make | Transom | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Operable | Clear/Restore | Paint shut | Missing | Repair/Make |  | Transom Glass | 43 | Priority 4
| Level 2 | 1 BEDROOM | Accessible | D2110 | Not applicable | Transom | Existing | Other | Clear/Restore | Transom | Existing | Clear/Restore |  | Existing | Repair/Make | Existing | Operable | Clear/Restore | Paint shut | Existing | Repair/Make |  | Transom Window | 27 | Priority 2
| Level 2 | 1 BEDROOM | Accessible | D2111 | Not applicable | Transom | Existing | Other | Clear/Restore | Transom | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Operable | Clear/Restore | Paint shut | Missing | Clear/Restore |  | Transom | 24 | Priority 2
| Level 2 | 1 BEDROOM | Accessible | D2112 | Not applicable | Transom | Missing | Other | Clear/Restore | Transom | Existing | Repair/Make |  | Missing | Clear/Restore | Existing | Operable | Clear/Restore | Paint shut | Existing | Clear/Restore |  |  | 35 | Priority 3
| Level 2 | 1 BEDROOM | Accessible | D2113 | Not applicable | Transom | Existing | Other | Repair/Make | Transom | Missing | Repair/Make |  | Existing | Clear/Restore | Existing | Operable | Clear/Restore |  | Missing | Clear/Restore |  |  | 40 | Priority 3
| Level 2 | 1 BEDROOM | Accessible | D2114 | Not applicable | Transom | Existing | Other | Clear/Restore | Transom | Existing | Repair/Make |  | Existing | Clear/Restore | Existing | Operable | Clear/Restore | Paint shut | Existing | Repair/Make |  |  | 27 | Priority 2
| Level 2 | 1 BEDROOM | Accessible | D2115 | Not applicable | Transom | Missing | Other | Repair/Make | Transom | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Operable | Clear/Restore | Paint shut | Existing | Clear/Restore |  |  | 34 | Priority 3
| Level 2 | 1 BEDROOM | Accessible | D2116 | Not applicable | Transom | Existing | Other | Clear/Restore | Transom | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Operable | Clear/Restore | Paint shut | Existing | Clear/Restore |  |  | 20 | Priority 2
| Level 2 | 1 BEDROOM | Accessible | D2117 | Not applicable | Transom | Existing | Other | Clear/Restore | Transom | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Operable | Clear/Restore | Paint shut | Existing | Clear/Restore |  |  | 20 | Priority 2
| Level 2 | 1 BEDROOM | Accessible | D2118 | Not applicable | Transom | Existing | Other | Clear/Restore | Transom | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Operable | Clear/Restore | Paint shut | Existing | Clear/Restore |  |  | 20 | Priority 2
| Level 2 | 1 BEDROOM | Accessible | D2120 | Not applicable | Transom | Existing | Other | Clear/Restore | Transom | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Operable | Clear/Restore | Paint shut. Broken glass | Existing | Clear/Restore |  |  | 20 | Priority 2
| Level 2 | 1 BEDROOM | Accessible | D2121 | Not applicable | Transom | Existing | Other | Clear/Restore | Transom | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Operable | Clear/Restore | Paint shut | Existing | Clear/Restore |  |  | 20 | Priority 2
| Level 2 | 1 BEDROOM | Accessible | D2122 | Not applicable | Transom | Existing | Other | Clear/Restore | Transom | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Operable | Clear/Restore | Paint shut | Existing | Clear/Restore |  |  | 20 | Priority 2
| Level 2 | 1 BEDROOM | Accessible | D2123 | Not applicable | Transom | Existing | Other | Clear/Restore | Transom | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Operable | Clear/Restore |  | Existing | Clear/Restore |  |  | 20 | Priority 2
| Level 2 | 1 BEDROOM | Accessible | D2124 | Not applicable | Transom | Existing | Other | Clear/Restore | Transom | Existing | Clear/Restore |  | Existing | Clear/Restore | Existing | Operable | Clear/Restore |  | Existing | Clear/Restore |  |  | 20 | Priority 2

## Qualification
ID Door | Door Origin | Door Type | Door - Current Status | Door - Recommended Action | Frame - Current Status | Frame - Recommended Action | Hinges - Current Status | Hinges - Recommended Action | Transom - Current Status | Transom - Function | Transom - Recommended Action | Door handle - Current Status | Door handle - Recommended Action | Automatic closing arm - Current Status | Total | Priority
D0001 | Original Door | Double Door | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 0 | 4 | 4 | 9 | 0 | 25 | Priority 2
D0002 | Original Door | Single Door | 9 | 9 | 0 | 2 | 4 | 4 | 0 | 0 | 0 | 4 | 9 | 0 | 41 | Priority 4
D0004 | Original Door | Single Door | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 4 | 9 | 0 | 21 | Priority 2
D0005 | Original Door | Single Door | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 4 | 9 | 0 | 21 | Priority 2
D0006 | Original Door | Single Door | 0 | 9 | 9 | 2 | 0 | 2 | 0 | 0 | 0 | 4 | 9 | 0 | 35 | Priority 3
D0007 | Not applicable | Single Door | 9 | 9 | 0 | 2 | 4 | 4 | 0 | 0 | 0 | 4 | 9 | 0 | 41 | Priority 4
D0008 | Not applicable | Single Door | 9 | 9 | 0 | 2 | 4 | 4 | 0 | 0 | 0 | 4 | 9 | 0 | 41 | Priority 4
D0009 | Not applicable | Single Door | 9 | 9 | 0 | 2 | 4 | 4 | 0 | 0 | 0 | 4 | 9 | 0 | 41 | Priority 4
D0003 | Original Door | Single Door | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 4 | 9 | 0 | 21 | Priority 2
D1001 | New Door | Double Door | 9 | 9 | 9 | 4 | 4 | 4 | 0 | 0 | 0 | 4 | 9 | 0 | 52 | Priority 4
D1002 | New Door | Double Door | 9 | 9 | 9 | 4 | 4 | 4 | 0 | 0 | 0 | 4 | 9 | 0 | 52 | Priority 4
D1003 | Original Door | Double Door | 9 | 9 | 9 | 4 | 4 | 4 | 0 | 0 | 0 | 4 | 9 | 0 | 52 | Priority 4
D1004 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1006 | New Door | Single Door | 9 | 9 | 0 | 2 | 4 | 4 | 0 | 0 | 4 | 4 | 9 | 0 | 45 | Priority 4
D1009 | Original Door | Single Door | 0 | 4 | 0 | 2 | 4 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 18 | Priority 1
D1010 | Original Door | Single Door | 0 | 9 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 4 | 9 | 0 | 26 | Priority 2
D1011 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1012 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1013 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1014 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1015 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1016 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1017 | Original Door | Single Door | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 4 | 0 | 12 | Priority 1
D1019 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1020 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1021 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1022 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1023 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1024 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1025 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1026 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1028 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1029 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1030 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1031 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1032 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1033 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1034 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1035 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1036 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1037 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1038 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1039 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1040 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1041 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1043 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1045 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1046 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1047 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1048 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1049 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1050 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1051 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1052 | New Door | Double Door | 9 | 9 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 4 | 9 | 0 | 43 | Priority 4
D1053 | Original Door | Double Door | 9 | 9 | 9 | 4 | 4 | 4 | 0 | 0 | 0 | 4 | 9 | 0 | 52 | Priority 4
D1054 | Original Door | Single Door | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 0 | 4 | 4 | 9 | 0 | 25 | Priority 2
D1055 | Original Door | Single Door | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 16 | Priority 1
D1056 | Original Door | Single Door | 0 | 4 | 0 | 2 | 4 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 22 | Priority 2
D1057 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1058 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1059 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D1060 | Original Door | Single Door | 0 | 9 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 4 | 9 | 0 | 26 | Priority 2
D2001 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2002 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2003 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2004 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2005 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2006 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2007 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2008 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2009 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2010 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2011 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2012 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2013 | Original Door | Double Door | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 0 | 4 | 4 | 9 | 0 | 25 | Priority 2
D2014 | Original Door | Double Door | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 0 | 4 | 4 | 9 | 0 | 25 | Priority 2
D2015 | Original Door | Double Door | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 0 | 4 | 4 | 9 | 0 | 25 | Priority 2
D2016 | Original Door | Double Door | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 0 | 4 | 4 | 9 | 2 | 27 | Priority 2
D2017 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2018 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2019 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2020 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2021 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2022 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2023 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2024 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2025 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2026 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2027 | Original Door | Single Door | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 4 | 4 | 4 | 9 | 0 | 29 | Priority 2
D2028 | Original Door | Single Door | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 4 | 4 | 4 | 9 | 0 | 29 | Priority 2
D2029 | Original Door | Single Door | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 4 | 4 | 4 | 9 | 2 | 31 | Priority 3
D2030 | Original Door | Single Door | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 4 | 4 | 4 | 9 | 0 | 29 | Priority 2
D2031 | Original Door | Single Door | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 4 | 4 | 4 | 9 | 2 | 31 | Priority 3
D2032 | Original Door | Single Door | 0 | 4 | 0 | 4 | 0 | 2 | 0 | 4 | 4 | 4 | 9 | 2 | 33 | Priority 3
D2033 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2034 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2035 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2037 | Original Door | Single Door | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 4 | 4 | 4 | 9 | 0 | 29 | Priority 2
D2038 | Original Door | Single Door | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 4 | 4 | 0 | 9 | 2 | 27 | Priority 2
D2039 | New Door | Single Door | 9 | 9 | 0 | 4 | 4 | 4 | 0 | 4 | 4 | 4 | 9 | 0 | 51 | Priority 4
D2040 | Original Door | Single Door | 0 | 4 | 0 | 4 | 0 | 2 | 0 | 4 | 4 | 4 | 9 | 2 | 33 | Priority 3
D2041 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2042 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2043 | Original Door | Double Door | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 0 | 4 | 4 | 9 | 0 | 25 | Priority 2
D2044 | Original Door | Double Door | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 0 | 4 | 4 | 9 | 0 | 25 | Priority 2
D2045 | New Door | Single Door | 9 | 9 | 0 | 2 | 4 | 4 | 0 | 4 | 4 | 4 | 9 | 0 | 49 | Priority 4
D2046 | Original Door | Single Door | 0 | 4 | 0 | 4 | 0 | 2 | 0 | 4 | 4 | 4 | 9 | 0 | 31 | Priority 3
D2047 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2049 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2050 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2051 | Original Door | Single Door | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 4 | 4 | 4 | 9 | 0 | 29 | Priority 2
D2052 | Original Door | Single Door | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 4 | 4 | 4 | 9 | 2 | 31 | Priority 3
D2053 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2054 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2055 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2056 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2057 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2058 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2059 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2060 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2061 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2062 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2063 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2064 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2065 | New Door | Single Door | 0 | 4 | 0 | 2 | 0 | 4 | 0 | 4 | 4 | 4 | 9 | 0 | 31 | Priority 3
D2066 | Original Door | Single Door | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 4 | 4 | 4 | 9 | 0 | 29 | Priority 2
D2067 | Original Door | Single Door | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 4 | 4 | 4 | 9 | 0 | 29 | Priority 2
D2068 | Original Door | Single Door | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 4 | 4 | 4 | 9 | 2 | 31 | Priority 3
D2069 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2070 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2071 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2072 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2073 | Original Door | Double Door | 0 | 4 | 0 | 2 | 0 | 4 | 0 | 0 | 4 | 4 | 9 | 0 | 27 | Priority 2
D2073 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2074 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2076 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2077 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2078 | Original Door | Double Door | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 0 | 4 | 4 | 9 | 0 | 25 | Priority 2
D2080 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2081 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2082 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2084 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2085 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2086 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2088 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2089 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2090 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2091 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2092 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2093 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2094 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2095 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2096 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2097 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2099 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2100 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2101 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2102 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2103 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2104 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2105 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2106 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2107_1 | Original Door | Single Door | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 4 | 0 | 12 | Priority 1
D2107_2 | Original Door | Single Door | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 4 | 9 | 0 | 21 | Priority 2
D2108 | Original Door | Single Door | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 9 | 0 | 17 | Priority 1
D3001 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D3002 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D3003 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D3004 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D3005 | New Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Verifiable
D2119 | Not applicable | Transom | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 4 | 4 | 0 | 9 | 0 | 25 | Priority 2
D2109 | Not applicable | Transom | 9 | 9 | 0 | 2 | 0 | 2 | 0 | 4 | 4 | 4 | 9 | 0 | 43 | Priority 4
D2110 | Not applicable | Transom | 0 | 4 | 0 | 2 | 0 | 4 | 0 | 4 | 4 | 0 | 9 | 0 | 27 | Priority 2
D2111 | Not applicable | Transom | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 4 | 4 | 4 | 4 | 0 | 24 | Priority 2
D2112 | Not applicable | Transom | 9 | 4 | 0 | 4 | 4 | 2 | 0 | 4 | 4 | 0 | 4 | 0 | 35 | Priority 3
D2113 | Not applicable | Transom | 0 | 9 | 9 | 4 | 0 | 2 | 0 | 4 | 4 | 4 | 4 | 0 | 40 | Priority 3
D2114 | Not applicable | Transom | 0 | 4 | 0 | 4 | 0 | 2 | 0 | 4 | 4 | 0 | 9 | 0 | 27 | Priority 2
D2115 | Not applicable | Transom | 9 | 9 | 0 | 2 | 0 | 2 | 0 | 4 | 4 | 0 | 4 | 0 | 34 | Priority 3
D2116 | Not applicable | Transom | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 4 | 4 | 0 | 4 | 0 | 20 | Priority 2
D2117 | Not applicable | Transom | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 4 | 4 | 0 | 4 | 0 | 20 | Priority 2
D2118 | Not applicable | Transom | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 4 | 4 | 0 | 4 | 0 | 20 | Priority 2
D2120 | Not applicable | Transom | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 4 | 4 | 0 | 4 | 0 | 20 | Priority 2
D2121 | Not applicable | Transom | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 4 | 4 | 0 | 4 | 0 | 20 | Priority 2
D2122 | Not applicable | Transom | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 4 | 4 | 0 | 4 | 0 | 20 | Priority 2
D2123 | Not applicable | Transom | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 4 | 4 | 0 | 4 | 0 | 20 | Priority 2
D2124 | Not applicable | Transom | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 4 | 4 | 0 | 4 | 0 | 20 | Priority 2

## Calculate
Priority Type | Total x Priority
Priority 1 | 5
Priority 2 | 37
Priority 3 | 12
Priority 4 | 13
Not Verifiable | 119 | 8
0
11